## CAF Server Migrartion Project T
ID | Work Item Type | Title 1 | Title 2 | Title 3 | Title 4 | Priority | Assigned To | State | Iteration Path
205000 | Epic | CAF Server Migration Project Plan |  |  |  | 1 | Ganesh Pandian | Active | CAF Server Migration\20\20.01.1
205001 | Feature |  | Plan, Assessment & Designing |  |  | 2 | Ganesh Pandian | Active | CAF Server Migration\20\20.01.1
205002 | User Story |  |  | Define Strategy |  | 2 | Ganesh Pandian | Active | CAF Server Migration\20\20.01.1
205003 | Task |  |  |  | Define Strategy CAF Plan Template | 2 | Ganesh Pandian | Active | CAF Server Migration\20\20.01.1
205004 | Task |  |  |  | Inventory and Rationalize Digital Estate | 2 | Ganesh Pandian | Active | CAF Server Migration\20\20.01.1
205005 | User Story |  |  | Cloud Assessment |  | 2 | Ganesh Pandian | Active | CAF Server Migration\20\20.01.2
205006 | Task |  |  |  | Organizational alignment to support the Adaption plan | 2 | Ganesh Pandian | Active | CAF Server Migration\20\20.01.2
205007 | Task |  |  |  | Skills Readiness and Role Based Responsibilities | 2 | Ganesh Pandian | Active | CAF Server Migration\20\20.01.2
205008 | Task |  |  |  | Data requirement and Classification | 2 | Ganesh Pandian | Active | CAF Server Migration\20\20.01.3
205009 | Task |  |  |  | Businesss logic and Infrastructure dependencies | 2 | Ganesh Pandian | Active | CAF Server Migration\20\20.01.3
205010 | Task |  |  |  | Develop Cloud Adoption plan | 2 | Ganesh Pandian | Active | CAF Server Migration\20\20.01.3
205011 | User Story |  |  | CAF Server Migration Design |  | 2 | Ganesh Pandian | Active | CAF Server Migration\20\20.01.4
205012 | Task |  |  |  | Detailed migration plan and effort documentation | 2 | Ganesh Pandian | Active | CAF Server Migration\20\20.01.4
205013 | Task |  |  |  | Network Topology Desiging | 2 | Ganesh Pandian | Active | CAF Server Migration\20\20.01.4
205014 | Task |  |  |  | Security and Tisk Assessment | 2 | Ganesh Pandian | Active | CAF Server Migration\20\20.01.4
205015 | Task |  |  |  | Planning, Assessement & Desiging review and SignOff | 2 | Ganesh Pandian | Active | CAF Server Migration\20\20.01.4
205016 | Feature |  | CAF Server Pre-Config & Migration |  |  | 2 | Ganesh Pandian | Active | CAF Server Migration\20\20.02.1
205017 | User Story |  |  | Server Migration Pre-Configuration |  | 2 | Ganesh Pandian | Active | CAF Server Migration\20\20.02.1
205018 | Task |  |  |  | Create Pre-configuration documentation and Change Request | 2 | Ganesh Pandian | Active | CAF Server Migration\20\20.02.1
205019 | Task |  |  |  | Prep on-prem Infrastructure | 2 | Ganesh Pandian | Active | CAF Server Migration\20\20.02.1
205020 | Task |  |  |  | Azure Setup and Configuration | 2 | Ganesh Pandian | Active | CAF Server Migration\20\20.02.1
205021 | Task |  |  |  | Azure Cloud Resources | 2 | Ganesh Pandian | Active | CAF Server Migration\20\20.02.1
205022 | Task |  |  |  | Azure Subscription target | 2 | Ganesh Pandian | Active | CAF Server Migration\20\20.02.1
205023 | Task |  |  |  | Azure Role Based Access | 2 | Ganesh Pandian | Active | CAF Server Migration\20\20.02.1
205024 | Task |  |  |  | Managing Access | 2 | Ganesh Pandian | Active | CAF Server Migration\20\20.02.1
205025 | Task |  |  |  | Azure tools and Approaches | 2 | Ganesh Pandian | Active | CAF Server Migration\20\20.02.1
205026 | Task |  |  |  | Azure Migration Readiness | 2 | Ganesh Pandian | Active | CAF Server Migration\20\20.02.2
205027 | Task |  |  |  | Site-to-Site Connectivity Summary | 2 | Ganesh Pandian | Active | CAF Server Migration\20\20.02.2
205028 | Task |  |  |  | Cost and Billing of Azure resources | 2 | Ganesh Pandian | Active | CAF Server Migration\20\20.02.2
205029 | User Story |  |  | Adopt (Migrate) |  | 2 | Ganesh Pandian | Active | CAF Server Migration\20\20.02.3
205030 | Task |  |  |  | Migration Pre-requirement configuration and validation | 2 | Ganesh Pandian | Active | CAF Server Migration\20\20.02.3
205031 | Task |  |  |  | Migration Strategy | 2 | Ganesh Pandian | Active | CAF Server Migration\20\20.02.3
205032 | Task |  |  |  | Migration: Deployment | 2 | Ganesh Pandian | Active | CAF Server Migration\20\20.02.3
205033 | Task |  |  |  | Migration: Infrastructure Integration | 2 | Ganesh Pandian | Active | CAF Server Migration\20\20.02.3
205034 | Task |  |  |  | Migration: Application Integration | 2 | Ganesh Pandian | Active | CAF Server Migration\20\20.02.3
205035 | User Story |  |  | Migration of On-Prem to Azure |  | 2 | Ganesh Pandian | Active | CAF Server Migration\20\20.02.4
205036 | Task |  |  |  | Prepare the Physical Server Assessment and requirement | 2 | Ganesh Pandian | Active | CAF Server Migration\20\20.02.4
205037 | Task |  |  |  | Configure the Azure envirnment based on the assessment | 2 | Ganesh Pandian | Active | CAF Server Migration\20\20.02.4
205038 | Task |  |  |  | Migrate Physical Servers to Azure | 2 | Ganesh Pandian | Active | CAF Server Migration\20\20.02.4
205039 | Task |  |  |  | Test and Validate the physical server migration to Azure | 2 | Ganesh Pandian | Active | CAF Server Migration\20\20.02.4
205040 | User Story |  |  | Migration of Hyper-V to Azure |  | 2 | Ganesh Pandian | Active | CAF Server Migration\20\20.03.1
205041 | Task |  |  |  | Prepare the Hyper V Host and Virtual Server Assessment and requirement | 2 | Ganesh Pandian | Active | CAF Server Migration\20\20.03.1
205042 | Task |  |  |  | Configure the Azure envirnment based on the assessment | 2 | Ganesh Pandian | Active | CAF Server Migration\20\20.03.1
205043 | Task |  |  |  | Migrate Hyper V Host and Virtual Servers to Azure | 2 | Ganesh Pandian | Active | CAF Server Migration\20\20.03.1
205044 | Task |  |  |  | Test and Validate the Hyper V Host and Virtual server migration to Azure | 2 | Ganesh Pandian | Active | CAF Server Migration\20\20.03.1
205045 | User Story |  |  | Migration of VMware to Azure |  | 2 | Ganesh Pandian | Active | CAF Server Migration\20\20.03.2
205046 | Task |  |  |  | Prepare the VMWare Virtual Server Assessment and requirement | 2 | Ganesh Pandian | Active | CAF Server Migration\20\20.03.2
205047 | Task |  |  |  | Configure the Azure envirnment based on the assessment | 2 | Ganesh Pandian | Active | CAF Server Migration\20\20.03.2
205048 | Task |  |  |  | Migrate VMWare Virtual Servers to Azure
205049 | Task |  |  |  | Test and Validate the VMWare Virtual server migration to Azure | 2 | Ganesh Pandian | Active | CAF Server Migration\20\20.03.2
205050 | Task |  |  |  | Migration: Documentation of implementation and Change request for performing the activity | 2 | Ganesh Pandian | Active | CAF Server Migration\20\20.03.2
205051 | Feature |  | CAF Server Migration Govern and Security |  |  | 2 | Ganesh Pandian | Active | CAF Server Migration\20\20.03.3
205052 | User Story |  |  | Server Migration Transition |  |  | Ganesh Pandian | Active | CAF Server Migration\20\20.03.3
205053 | Task |  |  |  | Server migration Functional Validation | 2 | Ganesh Pandian | Active | CAF Server Migration\20\20.03.3
205054 | Task |  |  |  | Transition to Support | 2 | Ganesh Pandian | Active | CAF Server Migration\20\20.03.3
205055 | Task |  |  |  | Release Management | 2 | Ganesh Pandian | Active | CAF Server Migration\20\20.03.3
205056 | User Story |  |  | Govern |  | 2 | Ganesh Pandian | Active | CAF Server Migration\20\20.03.4
205057 | Task |  |  |  | Governance | 2 | Ganesh Pandian | Active | CAF Server Migration\20\20.03.4
205058 | Task |  |  |  | Security Implemtation and reporting | 2 | Ganesh Pandian | Active | CAF Server Migration\20\20.03.4
205059 | Task |  |  |  | Compliance | 2 | Ganesh Pandian | Active | CAF Server Migration\20\20.03.4
205060 | Feature |  | CAF Migration Operation and Support |  |  | 2 | Ganesh Pandian | Active | CAF Server Migration\20\20.03.5
205061 | User Story |  |  | Manage |  | 2 | Ganesh Pandian | Active | CAF Server Migration\20\20.03.5
205062 | Task |  |  |  | Inventory and visibility | 2 | Ganesh Pandian | Active | CAF Server Migration\20\20.03.5
205063 | Task |  |  |  | Operational compliance | 2 | Ganesh Pandian | Active | CAF Server Migration\20\20.03.5
205064 | Task |  |  |  | Protect and recover | 2 | Ganesh Pandian | Active | CAF Server Migration\20\20.03.5
205065 | Task |  |  |  | Cutover and Decommission | 2 | Ganesh Pandian | Active | CAF Server Migration\20\20.03.5
205066 | User Story |  |  | Monitoring and Reporting |  | 2 | Ganesh Pandian | Active | CAF Server Migration\20\20.04.1
205067 | Task |  |  |  | Configure Monitoring System | 2 | Ganesh Pandian | Active | CAF Server Migration\20\20.04.1
205068 | Task |  |  |  | Configure Report Building | 2 | Ganesh Pandian | Active | CAF Server Migration\20\20.04.2
205069 | Task |  |  |  | Automation of reporting and alerting configuration | 2 | Ganesh Pandian | Active | CAF Server Migration\20\20.04.3
205070 | Task |  |  |  | Documentation of monitoring and reporting process | 2 | Ganesh Pandian | Active | CAF Server Migration\20\20.04.3
205071 | Feature |  | STAKEHOLDER SIGN OFF AND CLOSURE |  |  | 2 | Ganesh Pandian | Active | CAF Server Migration\20\20.04.4
205072 | User Story |  |  | CAF Server Migration Project Review and Clouser |  |  | Ganesh Pandian | Active | CAF Server Migration\20\20.04.4
205073 | Task |  |  |  | Server Migration Project review meeting |  | Ganesh Pandian | Active | CAF Server Migration\20\20.04.4
205074 | Task |  |  |  | Server Migration Project documentation and Supported documents review |  | Ganesh Pandian | Active | CAF Server Migration\20\20.04.4
205075 | Task |  |  |  | Lessons Learnt documentation, Troubleshooting Guide for future supporting | 2 | Ganesh Pandian | Active | CAF Server Migration\20\20.04.4
205076 | Task |  |  |  | Sign off on Project delivery | 2 | Ganesh Pandian | Active | CAF Server Migration\20\20.04.4

## Sheet1
| Epic | Ready
205016 | Feature | Rehost |  |  | 2 | Ganesh Pandian | Active | CAF Server Migration\20\20.02.1
205017 | User Story |  | Server Migration Pre-Configuration |  | 2 | Ganesh Pandian | Active | CAF Server Migration\20\20.02.1
205018 | Task |  |  | Create Pre-configuration documentation and Change Request | 2 | Ganesh Pandian | Active | CAF Server Migration\20\20.02.1
205019 | Task |  |  | Prep on-prem Infrastructure | 2 | Ganesh Pandian | Active | CAF Server Migration\20\20.02.1
205020 | Task |  |  | Azure Setup and Configuration | 2 | Ganesh Pandian | Active | CAF Server Migration\20\20.02.1
205021 | Task |  |  | Azure Cloud Resources | 2 | Ganesh Pandian | Active | CAF Server Migration\20\20.02.1
205022 | Task |  |  | Azure Subscription target | 2 | Ganesh Pandian | Active | CAF Server Migration\20\20.02.1
205023 | Task |  |  | Azure Role Based Access | 2 | Ganesh Pandian | Active | CAF Server Migration\20\20.02.1
205024 | Task |  |  | Managing Access | 2 | Ganesh Pandian | Active | CAF Server Migration\20\20.02.1
205025 | Task |  |  | Azure tools and Approaches | 2 | Ganesh Pandian | Active | CAF Server Migration\20\20.02.1
205026 | Task |  |  | Azure Migration Readiness | 2 | Ganesh Pandian | Active | CAF Server Migration\20\20.02.2
205027 | Task |  |  | Site-to-Site Connectivity Summary | 2 | Ganesh Pandian | Active | CAF Server Migration\20\20.02.2
205028 | Task |  |  | Cost and Billing of Azure resources | 2 | Ganesh Pandian | Active | CAF Server Migration\20\20.02.2
| Epic | Adopt
| Feature | Rehost
User Story
Task
Task
| Feature | Migrate
User Story
Task
Task
| Feature | Greenfield
User Story
Task
Task